## Iteration_Schedule
#Iteration | Start Date | End Date
1 | 2021-10-04 | 2021-10-22
2 | 2021-10-25 | 2021-11-12
3 | 2021-11-15 | 2021-12-03
4 | 2021-12-06 | 2021-12-24

## Mule_Contract_Tracking
API Integrations from Optimus Platform
Sr No | Iteration No | Expected Delivery Date from Mule | Integration API | Consumer System | Provider System | API Name | Endpoint | ESB | Integratiion Status | Request/Response type | Requires callback url | Integratioin POC | Remarks | MuleSoft API Spec Received ? | Autherization
1 | Iteration 3 | 2021-10-22 | Digilocker API to fetch KYC Documents like passport, voterId, DL etc | Optimus | Digilocker |  |  | MuleSoft | New | XML |  | Sreejesh Pillai | `-MuleWrapped to be developed to convert XML to JSON -Sreejesh Pillai - Owner of Digilocker Integration | No
2 | Iteration 1 | Received from Mule | NSDL PAN verification API | Optimus | NSDL | verifyPAN | https://esbmuat.idfcfirstbank.com:31297/util-mgmt/v1/verifyPAN | MuleSoft | Existing | JSON |  |  |  | Yes | Basic with Client-credentails
3 | Iteration 3 | Received from Mule | Enquire customer using UCIC | Optimus | CBS | enqCust | https://esbmuat.idfcfirstbank.com:31297/cust-mgmt/v1/enqCust | MuleSoft | New | JSON |  |  | `- Existing in MuleSoft, Spec to be shared by Mandar | Yes | Basic with Client-credentails
4 | Iteration 2 | Received from Mule | De-dupe API to get customer UCIC | Optimus | Posidex | checkGenericDedupe | https://esbmuat.idfcfirstbank.com:31297/cust-mgmt/v3.1/checkGenericDedupe | MuleSoft | Existing | JSON |  | Tushar Sinha | Specs required with valid end point url | Yes | Basic with Client-credentails
5 | Iteration 2 | Received from Mule | Mobile De-dupe check | Optimus | CBS | dedupeByMob | https://esbmuat.idfcfirstbank.com:31297/dedupe-mgmt/v1/dedupeByMob | MuleSoft | Existing | JSON |  | Mitrabanu panda | `- API to be confirmed post discussion on de-dupe feature | No | Basic with Client-credentails
6 | Iteration 4 | 2021-11-15 | Read bank statement API | Optimus | Perfios |  |  | MuleSoft | New | XML/JSON |  | Sarang, Girish, Czaee | ` - API name , API Spec to be shared by stakeholders from downstream systems - Mandar/ Rashi please find out if this API is listed in Mule Catalogue | Yes
7 | Iteration 3 | Received from Mule | Initiate penny drop to customer account number | Optimus | Benevalidation/ Karza | bankAccountVerification | https://esbmuat.idfcfirstbank.com:31297/util-mgmt/v1/enqGST | MuleSoft | New | JSON | Provider details required |  | `- Mandar to validate if API existing wthin bank systems for this. | No | Basic with Client-credentails
8 | Iteration 1 | Received from Mule | Verify GST details using Karza API | Optimus | Karza | enqGST | https://esbmuat.idfcfirstbank.com:31297/util-mgmt/v1/bankAccountVerification | MuleSoft | New | JSON |  |  |  | Yes | Basic with Client-credentails
| Iteration 1 | Received from Mule | Verify Driving License | Optimus | Karza | driversLicenceVerification | https://esbmuat.idfcfirstbank.com:31297/util-mgmt/v1/driversLicenceVerification | MuleSoft | New | JSON |  |  |  |  | Basic with Client-credentails
| Iteration 1 | Received from Mule | Verify Passport | Optimus | Karza | passportVerification | https://esbmuat.idfcfirstbank.com:31297/util-mgmt/v1/passportVerification | MuleSoft | New | JSON |  |  |  |  | Basic with Client-credentails
9 | Iteration 1 | Received from Mule | Verify Voter ID | Optimus | Karza | voterIdVerification | https://esbmuat.idfcfirstbank.com:31297/util-mgmt/v1/voterIdVerification | MuleSoft | New | JSON |  | Sreejesh Pillai |  | No | Basic with Client-credentails
10 | Iteration 1 | Received from Mule | Upload documents to fileNet | Optimus | FileNet | bpm_uploadDocuments | https://muleuat.capitalfirst.com:8443/generic_api_gateway/v2/bpm_uploadDocuments | MuleSoft | Existing | JSON |  |  |  | No
11 | Iteration 4 | Received from Mule | Run Commerical Bureau | Optimus | Multibureau |  | http://10.5.21.102:8099/api/v1/bbg/commercial/bureau/getResponse | MuleSoft | Existing | JSON |  | Sarang, Girish | `- API to be confirmed post discussion on ETB/NTB feature | Yes
12 | Iteration 3 | Existing Optimus service | Send OTP to customer | Optimus | SMS Gateway | generateOTP | https://esbmuat.idfcfirstbank.com:31297/sms-mgmt/v1/generateOTP | MuleSoft | Existing | JSON |  |  | `- IMPS 2.0 api to be used for account validation | Yes | Basic with Client-credentails
13 | Iteration 3 | Existing Optimus service | Verify OTP to customer | Optimus | SMS Gateway | verifyOTP | https://esbmuat.idfcfirstbank.com:31297/sms-mgmt/v1/verifyOTP | MuleSoft | Existing | JSON |  | Jagan Konar, Jay Pensay | `- Specs required with valid end point url - Dev team to reach out to Jagan Konar, Jay Pensay - SMS Gateway /OTP team for details on text update on message - New API to be shared for OTP sending to customer | Existing Optimus service | Basic with Client-credentails
14 | Iteration 3 | Received from Mule | Run Hunter Check | Optimus | Hunter |  | http://10.4.1.188:8084/SFDCFINNONE/hunter/wrapper | MuleSoft | Existing | JSON |  | Jagan Konar, Jay Pensay | Specs required with valid end point url | Existing Optimus service
15 | Iteration 2 | Received from Mule | Aadhar valt (ADV) API to get Aadhar ref number | Optimus | AVD | insertToken | https://muleuat.capitalfirst.com:8443/api/v1/aadharVault/insertToken | MuleSoft | TBD | XML | Yes |  | MuleWrapped to be developed to convert XML to JSON | No
16 | Iteration 4 | 2021-11-15 | Get user information like name, employee id, branch details for BO user from LDAP | Optimus | [9 empty] | No
17 | Iteration 4 | 2021-11-15 | API to update kyc review date in case of update of KYC for ETB customer | Optimus | [9 empty] | Existing Optimus service
18 | Iteration 4 | 2021-11-15 | API to Check if account/UCIC of the individual or entity is dormant | Optimus | CBS | prefetchAccount | https://esbmuat.idfcfirstbank.com:31297/acct-enq/v1/prefetchAccount | [6 empty] | Existing Optimus service | Basic with Client-credentails
19 | Iteration 3 | 2021-11-15 | API to Give the customer re-kyc due date | Optimus | CBS |  |  | MuleSoft | New | XML | Yes, Callback user to be exposed by services to receive response from Perfios. Perfios to share API spec for buildiing mulewrapper | Mohnish (perfios vendor), Rashi, Mandar | `- MuleWrapped to be developed to convert XML to JSON - API Endpoint same for perfois integratoin only product code would change for CA journey | No
20 | Iteration 2 | 2021-10-22 | Validate KYC document using Simplify api | Optimus | [7 empty] | `-No direct API LDAP in MuleSoft |  | No
21 | Iteration 2 | 2021-10-22 | Get branch and bank details based on IFSC code | Optimus | [9 empty] | No
22 | Iteration 3 | Existing Optimus service | Send SMS | Optimus | SMS Gateway | sendSMS | https://esbmuat.idfcfirstbank.com:31297/sms-mgmt/v1/sendSMS | [6 empty] | No | Basic with Client-credentails
23 | Iteration 3 | Existing Optimus service | Send Email | Optimus | SMTP | sendEmail | https://api.uat.internal.idfcfirstbank.com/email-exp/v1/sendEmail | [6 empty] | No | Basic with Client-credentails
24 | Iteration 4 | 2021-11-15 | Get Branch manager name, cluster head name | Optimus |  |  |  | MuleSoft | New | TBD |  |  | Specs required with valid end point url | Yes
Note: List of apis are as per current discussion on the feature requirements with IDFC first business team, McK and PSL. The API list can change if there is any change in requirements from business or user stories finalised by PSL team post discussions. This is not the final list of API to be developed. The finalised API list is to be shared by PSL team architects after they conclude the tech solution, user story finalisations and post discussion with MuleSoft ESB and downstream systems.